## Worksheet
Project Name | Phase | Start Date | End Date | Status | Responsible Team
Website Redesign Project | Discovery & Planning | 2023-09-01 | 2023-09-15 | In Progress | Product Team
Website Redesign Project | Design Phase | 2023-09-16 | 2023-10-10 | Pending Review | Design Team
Website Redesign Project | Development Phase | 2023-10-11 | 2023-11-25 | Not Started | Frontend & Backend Team
Website Redesign Project | Testing & QA | 2023-11-26 | 2023-12-08 | Not Started | QA Team
Website Redesign Project | Launch & Handover | 2023-12-09 | 2023-12-15 | Not Started | Project Manager & Client Team
Data Migration Initiative | Data Assessment | 2023-10-01 | 2023-10-14 | In Progress | IT Infrastructure Team
Data Migration Initiative | Migration Execution | 2023-10-15 | 2023-11-05 | Not Started | Data Engineering Team
Data Migration Initiative | Validation & Reporting | 2023-11-06 | 2023-11-17 | Not Started | Data Quality Team
Data Migration Initiative | Closure & Review | 2023-11-18 | 2023-11-30 | Not Started | Project Lead & Stakeholders
Mobile App Development | Idea & Requirements Gathering | 2023-11-01 | 2023-11-24 | In Progress | Product Team & UX Researchers
Mobile App Development | UI/UX Design Phase | 2023-11-25 | 2024-01-05 | Not Started | Design Team
Mobile App Development | App Development & Testing | 2024-01-06 | 2024-03-15 | Not Started | Development Team & QA Engineers
Mobile App Development | App Store Submission & Launch | 2024-03-16 | 2024-03-31 | Not Started | Project Manager & Marketing Team
Customer Portal Enhancement | User Feedback Analysis | 2023-12-01 | 2023-12-15 | In Progress | User Experience Team & Analytics Team
Customer Portal Enhancement | Feature Implementation | 2023-12-16 | 2024-01-31 | Not Started | Full Stack Team & DevOps
Customer Portal Enhancement | User Acceptance Testing (UAT) | 2024-02-01 | 2024-03-15 | Not Started | Testing Team & Client Representatives
Customer Portal Enhancement | Deployment & Monitoring | 2024-03-16 | 2024-04-30 | Not Started | DevOps Team & Support Team
Sustainability Report 2024 | Data Collection & Validation | 2023-10-01 | 2023-11-30 | In Progress | Sustainability Team & Compliance Unit
Sustainability Report 2024 | Report Drafting & Internal Review | 2023-12-01 | 2024-01-31 | Not Started | Sustainability Writer & Legal Team
Sustainability Report 2024 | Executive Review & Finalization | 2024-02-01 | 2024-03-15 | Not Started | C-Level Executives & Board Members
Sustainability Report 2024 | Publication & Distribution | 2024-03-16 | 2024-03-31 | Not Started | Marketing Team & Communications Department
Cybersecurity Audit & Compliance Update | Audit Planning & Scoping | 2023-09-15 | 2023-10-15 | Completed | Cybersecurity Team & Legal Counsel
Cybersecurity Audit & Compliance Update | Internal Security Testing | 2023-10-16 | 2024-01-15 | In Progress | Cybersecurity Team & IT Operations
Cybersecurity Audit & Compliance Update | External Audit Coordination | 2024-01-16 | 2024-03-31 | Not Started | Audit Firm & Compliance Manager
Cybersecurity Audit & Compliance Update | Remediation & Final Report Submission | 2024-04-01 | 2024-05-31 | Not Started | Cybersecurity Team & Executive Board