## Worksheet
Project Timeline - Client Reporting
Phase / Milestone | Start Date | End Date | Status | Owner | Progress (%)
Project Initiation & Planning | 2024-01-05 | 2024-01-19 | Completed | Jane Smith | 100%
Requirement Gathering | 2024-01-20 | 2024-01-31 | Completed | John Doe | 100%
Design & Prototyping | 2024-02-01 | 2024-02-15 | In Progress | Sarah Lee | 75%
Development Phase 1 | 2024-02-16 | 2024-03-15 | In Progress | Mike Chen | 55%
Development Phase 2 | 2024-03-16 | 2024-04-15 | Delayed | Rachel Green | 35%
Testing & QA | 2024-04-16 | 2024-05-15 | Delayed | Tony Wong | 10%
User Training & Documentation | 2024-05-16 | 2024-05-31 | Pending | Lisa Park | 0%
Go-Live & Deployment | 2024-06-01 | 2024-06-15 | Pending | David Brown | 0%
Report Generated On: