## Worksheet
Project Timeline Report
Client View ¦ Prepared for: [Client Name] ¦ Reporting Period: [Start Date] to [End Date]
Phase / Milestone | Description | Planned Start | Planned End | Actual Start | Actual End | Status
Project Kickoff | Initial planning and team alignment. | 2023-10-01 | 2023-10-05 | 2023-10-01 | 2023-10-05 | Completed
Requirements Gathering | Capture and finalize client needs. | 2023-10-06 | 2023-10-15 | 2023-10-08 | 2023-10-14 | Completed
Design Phase | Create wireframes and UI/UX prototypes. | 2023-10-16 | 2023-10-30 | 2023-10-17 | 2023-10-29 | Completed
Development (Frontend) | Implement frontend components. | 2023-10-31 | 2023-11-15 | 2023-10-31 | - | In Progress
Development (Backend) | Build server-side logic and API integration. | 2023-11-01 | 2023-11-20 | 2023-11-05 | - | In Progress
Testing & QA | Conduct comprehensive testing cycles. | 2023-11-21 | 2023-12-05 | - | - | Pending Start
Client Review & Sign-off | Final approval from client. | 2023-12-06 | 2023-12-15 | - | - | Pending Start
Deployment & Go-Live | Launch project to production environment. | 2023-12-16 | 2023-12-31 | - | - | Pending Start