## Project Timeline Dashboard
Project Timeline Dashboard
Task ID | Task Name | Start Date | End Date | Status | Progress (%) | Responsible Team
PJ-001 | Project Initiation | 2024-03-01 | 2024-03-15 | Completed | 100% | Project Management
PJ-002 | Requirements Gathering | 2024-03-16 | 2024-03-31 | Completed | 100% | Business Analysts
PJ-003 | Design Phase | 2024-04-01 | 2024-04-15 | In Progress | 75% | UI/UX Team
PJ-004 | Development Sprint 1 | 2024-04-16 | 2024-05-15 | In Progress | 60% | Development Team
PJ-005 | Testing & QA | 2024-05-16 | 2024-06-15 | Delayed | 30% | QA Team
PJ-006 | User Training | 2024-06-16 | 2024-06-30 | In Progress | 50% | Training Team
PJ-007 | Go-Live & Deployment | 2024-07-01 | 2024-07-15 | Delayed | 15% | Operations Team
Project Summary
Total Tasks:7
Completed:2 (28.6%)
In Progress:4 (57.1%)
Delayed:2 (28.6%)
Status Indicator:On Track with Delays