## Worksheet
Phase | Task Name | Start Date | End Date | Status | Responsible Party | Budget (USD)
Planning | Project Initiation | 2024-01-05 | 2024-01-15 | In Progress | Jane Doe | $8,500.00
Design | UI/UX Design Phase 1 | 2024-01-16 | 2024-02-15 | To Do | Mike Smith | $15,750.00
Development | Frontend Development | 2024-02-16 | 2024-04-30 | To Do | Sarah Johnson | $35,900.00
Development | Backend Development | 2024-03-15 | 2024-05-31 | To Do | Tom Wilson | $45,600.00
Testing | QA Testing Phase 1 | 2024-05-15 | 2024-06-15 | To Do | Lisa Brown | $9,800.00
Deployment | Staging Deployment | 2024-06-16 | 2024-06-30 | To Do | Daniel Lee | $5,250.00
Deployment | Production Rollout | 2024-07-01 | 2024-07-15 | To Do | Daniel Lee | $3,500.00
Total Estimated Budget: | [5 empty] | $124,300.00