## Worksheet
Project Timeline - Detailed Client Report
Task ID | Task Description | Start Date | End Date | Milestones & Deliverables |  |  | Responsible Team | Status
|  |  |  | Target Date | Actual Date | Status Update
P001 | Project Kickoff & Planning | 2024-03-01 | 2024-03-15 | 2024-03-15 | — | On Track | Project Management Team | On Track
P002 | Requirement Gathering Workshop | 2024-03-16 | 2024-03-31 | 2024-03-31 | — | On Track | Business Analysts | On Track
P003 | Design Phase (UI/UX) | 2024-04-01 | 2024-05-15 | 2024-05-15 | — | On Track | Design Team | On Track
P004 | Backend Development (Phase 1) | 2024-05-16 | 2024-06-30 | 2024-06-30 | — | On Track | Backend Developers | On Track
P005 | Frontend Development (Phase 1) | 2024-06-15 | 2024-08-15 | 2024-08-15 | — | On Track | Frontend Developers | On Track
P006 | Integration & Testing (Sprint 1) | 2024-08-16 | 2024-09-30 | 2024-09-30 | — | On Track | QA & DevOps Team | On Track
P007 | User Acceptance Testing (UAT) | 2024-10-01 | 2024-11-30 | 2024-11-30 | — | On Track | Client & QA Team | On Track
P008 | Final Deployment & Go-Live | 2024-12-01 | 2024-12-31 | 2024-12-31 | — | On Track | DevOps & Project Team | On Track
Total Duration: | [6 empty] | 10 Months
Note:This timeline is updated as of March 15, 2024. All statuses reflect the current project progress and may be subject to change based on ongoing feedback and delivery cycles.