## Worksheet
Project | Client | Timeline Overview (Phases)
|  | Phase 1 Planning & Initiation | Phase 2 Design & Development | Phase 3 Testing & Review | Phase 4 Pilot Launch | Phase 5 Main Deployment | Total Duration (Days)
Digital Transformation Suite | GlobalTech Inc. | Start: Jan 5 End: Jan 20 | Start: Jan 21 End: Mar 15 | Start: Mar 16 End: Apr 20 | Start: Apr 21 End: May 5 | Start: May 6 End: Jun 30 | 146 days
Milestone: Requirements Sign-off - Jan 20, 2025 (Completed)
- Wireframes Approved - UI/UX Design Finalized - Backend Architecture Complete
Milestone: MVP Ready for Testing - Mar 15, 2025 (In Progress)