## Worksheet
Client Reporting - Project Timeline (Financial View)
Project Phase | Description | Start Date | End Date | Budget Allocated ($) | Actual Spend ($) | Status
Phase 1: Discovery & Planning | Initial project scoping, stakeholder interviews, and feasibility analysis. | 2024-04-01 | 2024-05-15 | 75,000.00 | 68,325.78 | On Track
Phase 2: Design | UI/UX wireframes, design prototypes, and client approval rounds. | 2024-05-16 | 2024-07-31 | 150,000.00 | 145,893.45 | On Track
Phase 3: Development | Frontend and backend development, API integration, database setup. | 2024-08-01 | 2025-01-15 | 675,000.00 | 398,476.22 | On Track
Phase 4: Testing | QA testing, user acceptance testing (UAT), bug fixes. | 2025-01-16 | 2025-03-31 | 95,000.00 | 78,944.67 | On Track
Phase 5: Deployment | Production rollout, data migration, go-live support. | 2025-04-01 | 2025-04-30 | 65,000.00 | 63,891.75 | On Track
Phase 6: Post-Launch Support | First 90 days of support, performance monitoring, minor enhancements. | 2025-05-01 | 2025-07-31 | 45,000.00 | 39,768.14 | On Track
Total Project Cost: |  |  |  | 1,105,000.00 | 835,399.91