## Freelancer Project Timeline
Freelancer Project Timeline
Task | Start Date | End Date | Status | Assigned To
Project Kickoff & Planning | 2024-01-15 | 2024-01-20 | In Progress | Jane Doe
Design Phase - Wireframes & Mockups | 2024-01-21 | 2024-01-31 | Pending | Mike Smith
Development - Frontend Implementation | 2024-02-01 | 2024-02-15 | Pending | Alex Johnson
Development - Backend Integration | 2024-02-16 | 2024-03-10 | Pending | Sarah Wilson
Testing & QA Cycle 1 | 2024-03-11 | 2024-03-25 | Pending | Lisa Brown
User Acceptance Testing (UAT) | 2024-03-26 | 2024-04-15 | Pending | Client Review
Final Deployment & Handover | 2024-04-16 | 2024-04-30 | Pending | Team Lead