## Worksheet
Project Timeline - Client Reporting
Task ID | Task Description | Start Date | End Date | Status | Assigned To | Budget (USD)
PJ001 | Project Kickoff & Planning | 2023-10-05 | 2023-10-15 | In Progress | Sarah Johnson | $7,500.00
PJ002 | Requirements Gathering | 2023-10-16 | 2023-11-15 | In Progress | Michael Chen | $9,800.00
PJ003 | Design Phase & Mockups | 2023-11-16 | 2024-01-15 | Pending | Lisa Park | $14,500.00
PJ004 | Development & Coding | 2024-01-16 | 2024-03-31 | Pending | Alex Rivera, Team 3 | $45,000.00
PJ005 | Testing & QA Validation | 2024-04-15 | 2024-05-15 | Pending | Nina Patel, QA Lead | $18,600.00
PJ006 | Client Review & Feedback | 2024-05-16 | 2024-05-31 | Pending | Daniel Kim, Client Liaison | $6,800.00
PJ007 | Deployment & Go-Live | 2024-06-15 | 2024-06-30 | Pending | Jamal Wallace, DevOps Team | $12,750.00
PJ008 | Post-Launch Support & Monitoring | 2024-07-15 | 2024-12-31 | Pending | Emily Liu, Support Team | $36,500.00
Total Project Budget:$151,450.00