## Worksheet
Project Phase | Planned Timeline |  | Actual Timeline | Progress Status | Owner
Start Date
Project Initiation | <2024-01-01Delayed ( +3 days ) | Jane Doe
Requirements Gathering | <2024-01-16Delayed ( +6 days ) | John Smith
Design Phase | <2024-02-08Delayed ( +3 days ) | Sarah Johnson
Development Phase | <2024-03-16Not Started (TBD)Delayed ( +14 days ) | Mike Brown
Testing & QA | <2024-06-01Not Started (TBD)Delayed ( +45 days ) | Anna Lee
Deployment & Go-Live | <2024-07-16Not Started (TBD)Delayed ( +65 days ) | Tony Garcia