## Worksheet
Monthly Project Timeline - Client Reporting
Month | Phase / Milestone | Start Date | End Date | Status | Responsible Team Member(s)
January 2024 | Project Kickoff & Planning | 01/05/2024 | 01/15/2024 | In Progress | John Doe, Sarah Lee
| Requirement Gathering & Documentation | 01/16/2024 | 01/31/2024 | In Progress | Sarah Lee, Michael Brown
| Initial Design Approval | 01/25/2024 | 01/31/2024 | Pending Review | Alice Kim, John Doe
February 2024 | System Architecture Development | 02/01/2024 | 02/15/2024 | Not Started | Michael Brown, David Chen
| Data Modeling & Database Setup | 02/16/2024 | 02/28/2024 | Not Started | Daniel Rodriguez, Alice Kim
| Milestone 1: Design Finalization & Sign-Off | 02/25/2024 | 02/28/2024 | Not Started | All Team Leads
March 2024 | Frontend Development Phase 1 | 03/01/2024 | 03/15/2024 | Not Started | Sarah Lee, Emily Wu
| Backend Development Phase 1 | 03/05/2024 | 03/20/2024 | Not Started | David Chen, Michael Brown
| Milestone 2: Prototype Completion & Review | 03/15/2024 | 03/31/2024 | Not Started | All Developers, Project Manager