## Worksheet
Project Timeline Report
Phase | Task Name | Start Date | End Date | Status | Responsible Team
Planning | Project Initiation | 2023-09-01 | 2023-09-07 | In Progress | Project Manager, Stakeholders
Milestones:
Kickoff Meeting - Completed on 2023-09-05 ¦ Requirements Finalized - Scheduled for 2023-09-14
Design | UI/UX Wireframes | 2023-09-10 | 2023-09-17 | Pending Review | Design Team, Product Owner
Milestones:
Wireframes Approved - Scheduled for 2023-09-21 ¦ Final Design Sign-off - Target: 2023-09-30
| Technical Architecture Design | 2023-09-18 | 2023-10-15 | In Progress | Dev Team, Lead Architect
Development | Frontend Implementation | 2023-10-16 | 2024-01-15 | Frontend Team
Critical Path Milestone
| Backend Development | 2023-10-16 | 2023-12-31 | Backend Team
Milestones:
Sprint 1 (Oct 2023) - Completed ¦ Sprint 2 (Nov 2023) - In Progress ¦ Sprint 3 (Dec 2023) - Scheduled
Project Timeline Report (Continued)
Phase | Task Name | Start Date | End Date | Status | Responsible Team
Development (Cont.) | API Integration | 2024-01-01 | 2024-01-31 | Backend & Frontend Teams
Milestones:
API V1 Complete - Target Date: 2024-01-25 ¦ Testing Begins - 2024-01-31
| Testing | System Integration Test (SIT) | 2024-02-01 | 2024-03-15 | QA Team
Milestones:
Test Cases Developed - Completed ¦ SIT Execution in Progress ¦ Defect Resolution Target: 2024-03-15
Project Timeline Report (Final)
Phase | Task Name | Start Date | End Date | Status | Responsible Team & Notes
Testing (Cont.) | User Acceptance Testing (UAT) | 2024-03-16 | 2024-05-15 | UAT Sign-off Target: 2024-05-15 ¦ Stakeholder Feedback Collection
Post-UAT Activities
| Final Bug Fixes & Patching | 2024-05-16 | 2024-05-31 | Critical Issues Resolved ¦ Release Candidate Finalized
Deployment | Staging Environment Setup | 2024-05-01 | 2024-05-15 | Infrastructure Ready ¦ Pre-release Validation Complete
Deployment Window
| Production Launch (Phase 1) | 2024-06-01 | 2024-06-15 | Go-live: June 5, 2024 ¦ Post-launch Monitoring Active
Post-Launch | Performance Monitoring & Optimization | 2024-06-16 | 2024-12-31 | System Stability Checks ¦ User Feedback Integration
Final Milestone
| Project Closure & Documentation Finalization | 2024-11-01 | 2024-12-31 | Final Report Submitted ¦ Knowledge Transfer Completed