## Project Timeline - Office Use
Project Timeline ReportClient: ABC Corporation ¦ Reporting Period: Q3 2024
Phase | Task Description | Start Date | End Date | Status | Responsible Team Member
1. Planning & Initiation | Project Kick-off Meeting and Scope Finalization | 2024-07-01 | 2024-07-15 | In Progress | Jane Smith (PM)
2. Design Phase | Wireframing and UI/UX Design Approval | 2024-07-16 | 2024-08-15 | Completed | Mark Lee (Design)
3. Development Phase | Frontend Implementation - Core Modules | 2024-08-16 | 2024-10-15 | In Progress | Sophia Brown (Dev)
3. Development Phase | Backend Integration and API Development | 2024-08-16 | 2024-10-31 | In Progress | David Kim (Dev)
4. Testing Phase | User Acceptance Testing (UAT) Preparation | 2024-10-31 | 2024-11-30 | Delayed - Awaiting Feedback from Client | Lisa Wong (QA)
5. Deployment | Staging Environment Deployment and Review | 2024-11-01 | 2024-11-30 | Completed | Tony Reed (DevOps)
6. Go-Live & Support | Production Launch and Initial Support Period | 2024-12-01 | 2025-01-31 | Planned - Not Started | Rachel Patel (Support)
Note:This timeline reflects projected dates and may be adjusted based on stakeholder feedback and resource availability. Status updates are reviewed weekly.