## Worksheet
Project Timeline - Client Reporting
Reporting Period: January 2024 - December 2024 ¦ Prepared on: April 5, 2024
Phase / Milestone | Start Date | End Date | Status | Responsible Team | Description
Project Initiation & Planning | Jan 01, 2024 | Jan 15, 2024 | Completed | Project Management | Defined project scope, objectives, and deliverables.
Requirements Gathering | Jan 16, 2024 | Feb 05, 2024 | Completed | Business Analysts | Clients and stakeholders provided input on functional needs.
Design & Prototyping | Feb 06, 2024 | Mar 15, 2024 | Completed | UI/UX Team | Developed wireframes and interactive prototypes for client review.
Development Phase 1 (Core Features) | Mar 16, 2024 | May 30, 2024 | In Progress | Development Team | Implementation of core application modules and reporting engine.
Testing & QA (UAT) | Jun 01, 2024 | Jul 15, 2024 | Delayed | QA Team | Final testing and client acceptance testing scheduled after feedback.
Deployment & Go-Live | Jul 16, 2024 | Aug 05, 2024 | Delayed | DevOps Team | Production deployment and final system validation.
Post-Launch Support & Optimization | Aug 06, 2024 | Dec 31, 2024 | Delayed | Support Team | Ongoing monitoring and performance tuning based on user feedback.