## Worksheet
Project Timeline - Client Reporting
Task | Start Date | End Date | Status | Responsible Team Member
Project Kickoff | 2024-01-05 | 2024-01-07 | In Progress | Alice Johnson
Requirements Gathering | 2024-01-08 | 2024-01-19 | Completed | Bob Smith
Design Phase | 2024-01-20 | 2024-01-31 | In Progress | Cathy Lee
Development Phase | 2024-02-01 | 2024-03-15 | Pending | Daniel Brown
Testing & QA | 2024-03-16 | 2024-04-15 | Pending | Eva Martinez
User Training & Documentation | 2024-04-16 | 2024-05-03 | Pending | Fred Wilson
Final Review & Client Approval | 2024-05-04 | 2024-05-11 | Pending | Gina Taylor
Project Closure & Handover | 2024-05-12 | 2024-05-15 | Pending | Hank Reed
Template Type: Project Timeline
Purpose: Client Reporting