## Worksheet
Project Timeline - Planning View
Task ID | Task Description | Start Date | End Date | Duration (days) | Responsible Team | Status
PT01 | Project Initiation & Planning | 2024-04-01 | 2024-04-15 | 15 | Project Management Office (PMO) | Completed
PT02 | Requirements Gathering & Analysis | 2024-04-16 | 2024-05-15 | 30 | Business Analysts, Stakeholders | Completed
PT03 | System Design & Architecture Finalization | 2024-05-16 | 2024-06-15 | 31 | Lead Architects, Dev Team | Completed
PT04 | Frontend Development (Phase 1) | 2024-06-16 | 2024-07-31 | 46 | Frontend Developers | In Progress
PT05 | Backend Development (Phase 1) | 2024-06-16 | 2024-07-31 | 46 | Backend Developers | In Progress
Milestone: MVP Ready for QA Testing (Target: 2024-08-15)
PT06 | Full Integration & System Testing | 2024-08-16 | 2024-09-30 | 45 | QA Team, DevOps | Delayed (Pending Dependency)
PT07 | User Acceptance Testing (UAT) | 2024-10-01 | 2024-10-31 | 30 | End Users, Product Team | Pending Start
PT08 | Final Bug Fixes & Optimization | 2024-11-01 | 2024-11-30 | 30 | Tech Support, Dev Team | Pending Start
Milestone: Project Go-Live (Target: 2024-12-01)
Legend:
Completed– Task has been finalized.
In Progress– Ongoing work with current focus.
Delayed (Pending Dependency)– Delayed due to external factors or dependencies.
Pending Start– Scheduled but not yet initiated.
Report generated on: