## Worksheet
Project Phase | Start Date | End Date | Status | Description | Responsible Team
Project Initiation | 2023-09-15 | 2023-09-30 | Completed | Defined objectives, scope, and stakeholders. | Project Management Office
Requirement Gathering | 2023-10-01 | 2023-10-15 | Completed | Collected and documented client requirements. | Business Analysts
Design Phase | 2023-10-16 | 2023-11-05 | Completed | Created wireframes and system architecture. | UI/UX Designers, Architects
Development (Frontend) | 2023-11-06 | 2023-12-15 | Ongoing | Implemented user interface components. | Frontend Developers
Development (Backend) | 2023-11-06 | 2024-01-15 | Ongoing | Developed server-side logic and APIs. | Backend Developers
Integration & Testing | 2024-01-16 | 2024-02-15 | Delayed | Integrated systems and conducted QA testing. | QA Team, DevOps Engineers
User Training & Documentation | 2024-02-16 | 2024-03-15 | Delayed | Prepared training materials and conducted sessions. | Training Specialists, Technical Writers
Deployment & Go-Live | 2024-03-16 | 2024-03-31 | Delayed | Launched system to production environment. | DevOps, Project Managers
Total Duration | 2023-09-15 to 2024-03-31 |  | Estimated Completion: 16 weeks (7 months)