## Worksheet
Client Reporting - Project Timeline (Quarterly)
Project | Phase / Task | Q1 Start Date | Q1 End Date | Q2 Start Date | Q2 End Date | Status & Progress (Current Quarter)
Client X - Website Redesign | Requirement Gathering | 2024-01-01 | 2024-03-31 | - | -
| UI/UX Design | 2024-01-15 | 2024-03-15 | - | -
Development & Testing | - | - | 2024-04-01 | 2024-06-30
Client Y - CRM Integration | System Audit & Planning | 2024-01-10 | 2024-03-31 | - | -
Implementation & Training | - | - | 2024-04-15 | 2024-06-30
Client Z - Mobile App Launch | Market Research & Feature Definition | 2024-01-01 | 2024-03-31 | - | -
| App Development | - | - | 2024-04-01 | 2024-06-30
Pre-Launch Testing & Marketing | - | - | 2024-07-01 | 2024-09-30
Key Metrics Summary (Q2 2024)
Total Projects Completed |  |  | 1 | -
On-Track Projects (Q2) |  |  | 4
Risks & Delays |  |  | 1 (CRM Integration - minor delay due to data migration)