## Worksheet
Project Phase | Start Date | End Date | Status | Assigned Team Member
Project Initiation | 2023-10-01 | 2023-10-07 | In Progress | Jane Doe
Requirements Gathering | 2023-10-08 | 2023-10-14 | Pending | John Smith
Design Phase | 2023-10-15 | 2023-10-28 | Pending | Sarah Lee
Development | 2023-10-29 | 2023-11-15 | Pending | Mike Johnson
Testing & QA | 2023-11-16 | 2023-11-25 | Pending | Lisa Wang
Deployment | 2023-11-26 | 2023-11-30 | Pending | Alex Brown
Total Duration | 56 days (2023-10-01 to 2023-11-30)