## Worksheet
Project ID | Task Name | Start Date | End Date | Status | Assigned To
PJ001 | Project Kickoff Meeting | 2024-04-05 | 2024-04-05 | Completed | Alice Johnson
PJ001 | Requirement Gathering & Analysis | 2024-04-08 | 2024-04-19 | In Progress | Robert Smith
Phase 1: Requirements Finalized (Milestone)
PJ001 | UI/UX Design | 2024-04-22 | 2024-05-15 | Not Started | Sophia Lee
PJ001 | Frontend Development | 2024-05-16 | 2024-06-30 | Not Started | James Brown
Phase 2: Design & Frontend Complete (Milestone)
PJ001 | Backend Development | 2024-06-17 | 2024-08-15 | Not Started | Laura Davis
PJ001 | Integration Testing | 2024-08-16 | 2024-09-15 | Not Started | Martin Wilson
Phase 3: Development Complete (Milestone)
PJ001 | User Acceptance Testing (UAT) | 2024-09-16 | 2024-10-31 | Not Started | Sarah Miller
PJ001 | Deployment & Go-Live | 2024-11-01 | 2024-11-05 | Not Started | Alice Johnson, Robert Smith
Final: Project Delivery & Client Sign-off (Milestone)