## Worksheet
Client Reporting - Project Timeline
Template Type: Project Timeline
Phase | Task Description | Start Date | End Date | Status | Responsible Team Member
Planning & Requirements | Gather client requirements and define project scope. | 2023-10-01 | 2023-10-15 | In Progress | John Doe
Design Phase | Create wireframes and UI/UX mockups. | 2023-10-16 | 2023-11-05 | Pending | Jane Smith
Development Phase | Build frontend and backend components. | 2023-11-06 | 2024-01-15 | Not Started | Alex Johnson
Testing & QA | Conduct functional and user acceptance testing. | 2024-01-16 | 2024-02-15 | Not Started | Sarah Williams
Deployment & Launch | Deploy to production and launch the project. | 2024-02-16 | 2024-03-01 | Not Started | Michael Brown