## Worksheet
Client Reporting - Weekly Project Timeline
Week Starting | Task/Activity | Description | Owner | Status (Weekly) | Milestone/Deadline
Week 1: January 1 - January 7, 2024
January 1, 2024 | Project Kickoff Meeting | Initial meeting with client to review project goals and deliverables. | Jane Smith (Project Manager) | On Track | January 3, 2024
January 2, 2024 | Requirements Gathering | Capture detailed client requirements and documentation. | Mike Johnson (Analyst) | On Track | January 6, 2024
Week 2: January 8 - January 14, 2024
January 9, 2024 | Design Phase Initiation | Create wireframes and UI mockups for client approval. | Sarah Lee (UI/UX Designer) | On Track | January 13, 2024
January 10, 2024 | Backend Architecture Planning | Develop high-level system architecture and database schema. | Daniel Brown (Lead Developer) | On Track | January 14, 2024
Week 3: January 15 - January 21, 2024
January 16, 2024 | Client Review: UI Mockups | Presentation and feedback session on design mockups. | Sarah Lee (UI/UX Designer) | On Track | January 18, 2024
January 17, 2024 | Frontend Development (Phase 1) | Begin development of core frontend components. | Lisa White (Frontend Developer) | On Track | January 21, 2024
Week 4: January 22 - January 28, 2024
January 23, 2024 | Backend Development (Phase 1) | Implement core API endpoints and authentication. | Daniel Brown (Lead Developer) | On Track | January 27, 2024
January 25, 2024 | Milestone: Design Sign-Off | Formal approval of final UI/UX designs. | Sarah Lee (UI/UX Designer) | Completed | January 25, 2024
Week 5: January 29 - February 4, 2024
January 30, 2024 | Integration Testing (Frontend & Backend) | Test connectivity and data flow between components. | Taylor Reed (QA Engineer) | On Track | February 2, 2024
January 31, 2024 | User Acceptance Testing (UAT) Preparation | Prepare test cases and environment for client UAT. | Taylor Reed (QA Engineer) | On Track | February 1, 2024
Note:This timeline is subject to change based on client feedback and project scope adjustments. Status updated weekly on Fridays.