## Worksheet
Project Name | Client | Start Date | End Date | Status | Progress (%) | Budget ($) | Actual Spend ($) | Milestone Achieved
Website Redesign | Acme Corp | 2023-01-15 | 2023-06-30 | In Progress | 65 | 50,000 | 32,500 | UI/UX Design Completed
Digital Marketing Campaign | BrightFuture Inc. | 2023-02-01 | 2023-08-15 | On Hold | 45 | 35,000 | 15,750 | Social Media Strategy Finalized
CRM Integration Project | TechNova Solutions | 2023-03-10 | 2023-11-30 | Planning Phase | 15 | 75,000 | 11,250 | Preliminary Requirements Gathered
E-Commerce Platform Upgrade | Global Retailers Ltd. | 2023-04-20 | 2023-10-15 | Completed | 100 | 68,500 | 67,345 | All Functionalities Tested & Deployed
Data Analytics Dashboard | InnovatePro Group | 2023-05-05 | 2023-12-31 | In Progress | 78 | 45,000 | 35,100 | Data Modeling Complete