## Worksheet
Project ID | Project Name | Client Name | Start Date | Expected End Date | Status | Budget (USD) | Actual Cost (USD) | % Complete
PJ001 | Website Redesign | GlobalTech Inc. | 2023-10-01 | 2024-01-31 | In Progress | 50,000.00 | 38,567.45 | 78%
PJ002 | Mobile App Development | Sunrise Solutions | 2023-11-15 | 2024-06-30 | In Progress | 85,000.00 | 47,239.88 | 56%
PJ003 | Data Migration Project | FinServe Group | 2023-09-10 | 2024-01-15 | Completed | 35,000.00 | 33,897.62 | 100%
PJ004 | Cybersecurity Audit | Nexus Enterprises | 2023-12-01 | 2024-03-31 | On Hold | 45,000.00 | 8,756.34 | 19%
PJ005 | CRM System Integration | SalesPro LLC | 2023-10-20 | 2024-11-30 | In Planning | 65,000.00 | 1,245.78 | 3%