## Worksheet
PROJECT TRACKER - CLIENT REPORTING
Project ID | Client Name | Project Title | Start Date | Target End Date | Status | Milestone Progress (%) | Budget (USD) | Budget Used (USD) | Action Required
ACTIVE PROJECTS
PRJ-001 | GlobalTech Inc. | Enterprise CRM Integration | 2024-01-15 | 2024-06-30 | In Progress | 65% | $85,000.00 | $55,250.75 | Review API documentation and finalize data mapping.
PRJ-002 | Sunrise Marketing Co. | Digital Campaign Platform Upgrade | 2024-03-10 | 2024-11-15 | In Progress | 48% | $67,500.00 | $32,407.38 | Submit revised design mockups for client approval.
PRJ-003 | NexGen Solutions | Mobile App Redesign & Launch | 2024-01-28 | 2024-10-31 | Delayed | 35% | $98,750.00 | $34,562.19Address server migration issues; schedule technical review.
PENDING APPROVALS
PRJ-004 | UrbanRetail Group | E-commerce Backend Optimization | 2024-05-18 | 2025-01-31 | Pending Approval | 15% | $76,400.00$11,463.87Client review pending on Q2 deliverables.
COMPLETED PROJECTS (2024)
PRJ-005 | QuickServe Logistics | Delivery Routing System Redesign | 2023-11-14 | 2024-05-31 | Completed | 100% | $58,900.00$57,834.67Final report and feedback session scheduled.
PRJ-006 | AquaPure Water Systems | Sustainability Dashboard Development | 2024-01-30 | 2024-11-30 | Completed | 100% | $68,555.75$67,493.38Post-project evaluation submitted.
TOTALS: | [6 empty] | $452,105.75 | $260,012.84
Report generated on:¦ Prepared by: Project Management Office