## Worksheet
Project Tracker - Client Reporting
Overview Dashboard
PROJECT OVERVIEW
Project Name | Client | Status | Start Date | Expected End Date | Budget (USD)
Website Redesign 2024 | Acme Inc. | In Progress | Jan 15, 2024 | Mar 30, 2024 | $50,000.00
Mobile App Development | TechNova Solutions | On Hold | Feb 1, 2024 | Jun 30, 2024 | $85,000.00
Data Migration Project | Global Finance LLC | Completed | Jan 1, 2024 | Feb 28, 2024 | $35,000.00
Total Projects: |  |  |  |  | 3
Key Performance Indicators (KPIs)
KPI | Target | Actual | Status
% of Projects Delivered On Time | 90% | 85% | In Progress
Budget Adherence Rate | 95% | 92% | In Progress
Overall Performance:
Project Tracker - Client Reporting
Project Details & Milestones
PROJECT: WEBSITE REDESIGN 2024 (Acme Inc.)
Milestone | Due Date | Status | Owner | Progress (%) | Notes/Remarks
Initial Design Approval | Feb 5, 2024 | Completed | Jane Smith (Design) | 100% | Drafts reviewed and approved.
Frontend Development Complete | Feb 28, 2024 | In Progress | Mark Lee (Dev) | 75% | Responsive layout in progress.
Backend Integration | Mar 10, 2024 | Scheduled | Sarah Chen (Dev) | 0% | To begin after frontend completion.
Overall Status: |  |  | 75% | On Track
Project: Mobile App Development (TechNova Solutions)
PROJECT: MOBILE APP DEVELOPMENT (TechNova Solutions)
Milestone | Due Date | Status | Owner | Progress (%) | Notes/Remarks
User Research & Wireframes Finalized | Jan 20, 2024 | Completed | Lisa Park (UX) | 100% | Signed off by client.
App Prototype Ready | Feb 15, 2024 | In Progress | Matt Johnson (UX/Dev) | 60%
Overall Status: |  |  | 60% | On Track
Project Tracker - Client Reporting
Resource Allocation & Timeline View
RESOURCE ALLOCATION SUMMARY
Team Member | Role | Project Assigned | % Allocation | Current Task Status
Jane Smith | Lead Designer | Website Redesign 2024 | 100%
Mark Lee | Frontend Developer
Project Timeline Overview
PROJECT TIMELINE - MARCH 2024
Week | 1 | 2
Prepared for Client Reporting – Project Tracker Template ¦ Multi-Page Format
Generated on: