## Worksheet
Project Tracker - Client Reporting
Project ID | Client Name | Project Name | Status | Start Date | Expected End Date | Progress (%) | Budget (USD)
P001 | Global Tech Solutions | Website Redesign 2024 | In Progress | 2024-01-15 | 2024-06-30 | 65% | $45,000
P002 | Nexa Systems Inc. | Mobile App Development | Planning | 2024-03-10 | 2024-11-15 | 15% | $78,500
P003 | BlueWave Analytics | Data Migration & Integration | Testing Phase | 2024-02-01 | 2024-08-31 | 87% | $62,300
P004 | Sunrise Retail Group | E-commerce Platform Upgrade | On Hold | 2024-01-22 | 2024-10-15 | 43% | $58,900
P005 | Elite HealthCare | CRM System Implementation | Completed | 2024-04-15 | 2024-07-31 | 100% | $38,750