## Worksheet
CLIENT REPORTING - SCHEDULE PLANNER - ANALYSIS VIEW
Task ID | Task Name | Assigned To | Start Date | End Date | Status | % Complete | Budget (USD) | Actual Cost (USD) | Deadline Alert | Risk Level | Action Required
T001 | Project Kickoff Meeting | John Smith | 2024-01-15 | 2024-01-15 | Completed | 100% | $5,000 | $4,850 | No | Low | None
T002 | Design Phase Review | Sarah Johnson | 2024-01-16 | 2024-01-31 | In Progress | 75% | $8,500 | $6,450 | Yes (2 days) | Medium | Review feedback by 2024-01-31
T003 | Development Sprint 1 | Mike Chen | 2024-02-01 | 2024-02-15 | Scheduled | 0% | $15,000 | $0 | No | Low | Prepare sprint backlog by 2024-01-31
T004 | User Testing Session | Lisa Wong | 2024-03-15 | 2024-03-18 | Scheduled | 0% | $6,000 | $0 | Yes (3 days) | High | Schedule testers by 2024-03-11
T005 | Final Delivery & Handover | Robert Brown | 2024-04-15 | 2024-04-30 | Scheduled | 5% | $18,000 | $985 | Yes (7 days) | High | Preliminary review needed by 2024-04-12
Summary:Total Tasks: 5 ¦ Completed: 1 (20%) ¦ In Progress: 1 (20%) ¦ Scheduled: 3 (60%)
Last updated on January 14, 2024. For reporting purposes only.