## Worksheet
Client Reporting - Schedule Planner
Client View ¦ Quarterly Planning Template
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Budget (USD)
TASK-001 | Initial Consultation & Requirements Gathering | John Doe (Project Manager) | 2024-04-01 | 2024-04-15 | In Progress | $8,500.00
TASK-002 | Design Phase - Wireframes & Mockups | Sarah Lin (Designer) | 2024-04-16 | 2024-05-15 | Pending | $12,300.00
TASK-003 | Development - Frontend Implementation | Mike Chen (Frontend Dev) | 2024-05-16 | 2024-06-30 | Pending | $18,750.00
TASK-004 | Development - Backend Integration | Lisa Wang (Backend Dev) | 2024-06-15 | 2024-07-31 | Pending | $16,900.00
TASK-005 | Testing & QA Review Cycle 1 | David Park (QA Lead) | 2024-08-01 | 2024-08-15 | Pending | $6,450.00
TASK-006 | User Acceptance Testing (UAT) | Client Team | 2024-08-16 | 2024-08-31 | Pending | $5,200.00
TASK-007 | Final Deployment & Go-Live | Team Lead (DevOps) | 2024-09-01 | 2024-09-15 | Pending | $7,850.00
Total Estimated Budget: | [5 empty] | $85,950.00