## Worksheet
Client Reporting - Schedule Planner (Extended)
Project Timeline & Task Management Overview ¦ Updated: October 2023
Task ID | Task Name | Owner | Due Date Range |  |  | Priority |  | Status | Notes / Comments
|  |  | Start Date | Deadline | Completion Target | High (Red) | Medium (Amber)
T001 | Initial Client Discovery Meeting | Jane Smith | 2023-10-15 | 2023-10-17 | 2023-10-17 | High | Medium | In Progress | Gather requirements and project scope.
T002 | Project Proposal Drafting | Mark Johnson | 2023-10-18 | 2023-10-25 | 2023-10-24 | High | Medium | Not Started | Include budget, timeline, deliverables.
M001 | Proposal Approval Deadline | - | 2023-10-26 | Final Approval Date | October 26, 2023 | High | - | Expected Milestone | Client must sign off by end of day.
T003 | Design Phase Kickoff | Sarah Lee | 2023-10-27 | 2023-11-15 | November 14, 2023 | Medium | - | Not Started | Begin wireframing and UX mockups.
T004 | Development Sprint 1: Backend Setup | David Chen | 2023-11-16 | 2023-12-07 | December 7, 2023 | High | - | Not Started | API integration and database schema.
M002 | Sprint 1 Review Meeting | Scheduled: December 8, 2023 (10:00 AM) |  |  |  | Medium | - | Expected Milestone | Review deliverables and adjust scope.
T005 | User Testing & Feedback Collection | January 15, 2024 - January 31, 2024 |  | February 15, 2024 | - | Low | - | Not Started | Conduct UAT with selected clients.
Total Tasks |  | 5 | [5 empty] | 3 High, 1 Medium, 1 Low | 4 Not Started / 1 In Progress / 0 Completed