## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status
T001 | Project Kickoff Meeting | John Doe | 2023-10-02 | 2023-10-02 | Completed
T002 | Requirement Gathering | Jane Smith | 2023-10-03 | 2023-10-15 | In Progress
T003 | Design Phase | Mike Johnson | 2023-10-16 | 2023-11-05 | Pending
T004 | Development Sprint 1 | Sarah Lee | 2023-11-06 | 2023-11-27 | Pending
T005 | Testing & QA | David Brown | 2023-11-28 | 2023-12-15 | Pending