## Worksheet
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | Progress (%) | Priority | Notes
T001 | Project Kickoff Meeting | Jane Smith | 2023-10-02 | 2023-10-05 | In Progress | 60 | High | Initial planning and scope discussion.
T002 | Requirement Gathering | Mike Johnson | 2023-10-06 | 2023-10-15 | Pending | 0 | Medium | Client interviews scheduled.
T003 | Design Phase | Sarah Lee | 2023-10-16 | 2023-10-30 | Not Started | 0 | Low | Design mockups to be approved.
T004 | Development Sprint 1 | Alex Chen | 2023-10-31 | 2023-11-14 | Not Started | 0 | Low | Backend implementation.
T005 | Client Review Session | Jane Smith | 2023-11-15 | 2023-11-20 | Not Started | 0 | Medium | Review deliverables with client.
T006 | Testing & QA | David Kim | 2023-11-21 | 2023-12-05 | Not Started | 0 | Low | Final test cycle.
T007 | Deployment Preparation | Alex Chen | 2023-12-06 | 2023-12-10 | Not Started | 0 | Low | Final checks and documentation.
T008 | Final Deployment | David Kim | 2023-12-11 | 2023-12-15 | Not Started | 0 | Low | Go live on client environment.
Total |  |  |  |  | Average Progress | 16%