## Worksheet
Advanced Task Manager - Client Reporting
Task ID | Task Name | Description | Assigned To | Due Date | Status | Priority | Budget (USD)
TASK-001 | Client Website Redesign | Complete full redesign of client's corporate website with responsive layout. | Jane Smith | 2024-12-31 | In Progress | High | $8,500.00
TASK-002 | Quarterly Reporting Package | Compile and deliver comprehensive Q3 performance report with visualizations. | Michael Chen | 2024-11-15 | Pending Review | Medium | $3,200.00
TASK-003 | SEO Optimization Campaign | Perform keyword research and implement on-page SEO improvements. | Sarah Johnson | 2024-11-28 | Completed | High | $6,800.00
TASK-004 | Client Presentation Deck Update | Revise and finalize presentation materials for upcoming client meeting. | David Brown | 2024-11-18 | Overdue | High | $2,500.00
TASK-005 | Newsletter Development | Create monthly newsletter content and design layout. | Lisa Wong | 2024-11-30 | Pending Review | Low | $1,800.00
TASK-006 | CRM Integration Project | Integrate client's CRM system with marketing automation platform. | Robert Davis | 2025-01-15 | In Progress | High | $14,300.00
TASK-007 | Brand Guidelines Documentation | Update and organize brand guidelines for internal and external use. | Emily Taylor | 2024-12-10 | Completed | Medium | $4,100.00
TASK-008 | Competitor Analysis Report | Research and analyze competitors' strategies and market positioning. | James Wilson | 2024-11-25 | Pending Review | Medium | $3,600.00
TASK-011 | Mobile App Feature Updates | Implement requested features based on user feedback. | Amanda Miller | 2024-12-30 | In Progress | High | $11,750.00
TASK-012 | Client Onboarding Package | Create comprehensive onboarding materials for new clients. | Thomas King | 2024-11-30 | Completed | Low | $2,900.00
Summary Statistics
Total Tasks: | 12
Completed: | 4 (33.3%)
In Progress: | 3 (25.0%)
Pending Review: | 4 (33.3%)
Overdue Tasks: | 1 (8.3%)
Total Projected Budget:$65,450.00
Budget Spent (Estimated):$37,180.00 (56.8%)