## Worksheet
Client Reporting - Task Manager (Client View)
Project Name: Q4 Client Deliverables ¦ Report Date: October 26, 2023
Task ID | Task Name | Assigned To | Status | Due Date | Priority | Budget Allocated (USD)
TASK-001 | Website Redesign Mockups | Jane Smith | In Progress | 2023-11-05 | High | $2,500.00
TASK-002 | Data Migration Strategy | Michael Brown | Pending Review | 2023-11-10 | Medium | $3,800.00
TASK-003 | Campaign Analytics Dashboard | Sarah Johnson | Completed | 2023-10-25 | High | $4,200.00
TASK-004 | User Feedback Integration | David Lee | Overdue | 2023-10-20 | Urgent | $1,950.00
TASK-005 | API Documentation Update | Lisa Chen | In Progress | 2023-11-15 | Medium | $1,600.00
TASK-006 | Client Onboarding Kit Finalization | Elena Rodriguez | Pending Review | 2023-11-20 | Low | $950.00
Total Tasks: | [5 empty] | $14,950.00
Status Breakdown: | [5 empty] | In Progress (2) ¦ Completed (1) ¦ Overdue (1) ¦ Pending Review (2)