## Worksheet
Task ID | Client Name | Project | Task Description | Status | Due Date | Budget (USD) | Actual Cost (USD) | Progress (%)
001 | ABC Corporation | Website Redesign | Develop responsive landing page with SEO integration | In Progress | 2023-10-15 | $8,500.00 | $6,245.75 | 73%
002 | XYZ Inc. | Financial Audit | Review fiscal year 2023 financial statements and compliance | Pending Review | 2023-11-05 | $15,000.00 | $14,875.99 | 99%
003 | GlobalTech Solutions | CRM Implementation | Deploy Salesforce CRM with data migration and training | Completed | 2023-10-28 | $20,500.00 | $19,745.33 | 100%
004 | MetroBank Group | Payroll System Upgrade | Integrate new payroll software with HRIS system | In Progress | 2023-11-30 | $12,800.00 | $9,456.25 | 74%
005 | Alpha Retail LLC | E-commerce Optimization | Improve website conversion rate through UX enhancements | Not Started | 2023-12-10 | $5,500.00 | $0.00 | 0%
Total Budget | [6 empty] | $62,300.00
Total Actual Cost | [6 empty] | $50,323.32