## Worksheet
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | Priority | Progress (%)
T001 | Project Kickoff Meeting | John Doe | 2024-01-15 | 2024-01-17 | In Progress | High | 60
T002 | Requirement Gathering | Jane Smith | 2024-01-16 | 2024-01-31 | In Progress | Medium | 45
T003 | Design Phase - UI/UX | Alex Johnson | 2024-01-20 | 2024-02-10 | Not Started | High | 0
T004 | Backend Development | Maria Garcia | 2024-01-25 | 2024-03-15 | In Progress | Medium | 25
T005 | Testing & QA | Chris Brown | 2024-03-16 | 2024-04-15 | Pending | Low | 0
T006 | Deployment & Go-Live | Lisa Wong | 2024-04-16 | 2024-04-30 | Pending | Low | 0
Total Tasks: | [6 empty] | 45%