## Worksheet
Client Reporting - To-Do List (Planning View)
Project: Q3 Client Performance Analysis ¦ Period: July 1 - September 30, 2024
Task ID | Task Description | Responsible Team | Due Date | Priority | Status
TASK-001 | Gather client KPI data from CRM system | Data Analytics Team | 2024-07-15 | High | Not Started
TASK-002 | Review historical performance trends (Q1-Q2 2024) | Data Analytics Team | 2024-07-18 | High | Not Started
TASK-003 | Create draft report outline and template design | Report Design Team | 2024-07-25 | Medium | In Progress
TASK-004 | Conduct stakeholder interview with client success team | Client Engagement Team | 2024-07-28 | Medium | Not Started
TASK-005 | Compile monthly client performance metrics (July) | Data Analytics Team | 2024-08-10 | High | Not Started
TASK-006 | Integrate data visualizations into report draft | Report Design Team | 2024-08-15 | Medium | In Progress
TASK-007 | Internal review and feedback collection (Round 1) | Project Management Office | 2024-08-25 | Medium | Not Started
TASK-008 | Finalize client report (Version 1.0) | Report Design Team / PMO | 2024-09-15 | High | Not Started
TASK-009 | Schedule and deliver client presentation session | Client Engagement Team / PMO | 2024-09-25 | High | Not Started
TASK-010 | Document lessons learned and update process playbook | Project Management Office | 2024-10-05 | Low | Not Started