## Worksheet
Compliance Tracking - Business Plan
Executive Summary & Compliance Overview
Item ID | Compliance Area | Description | Status | Last Updated
CP-001 | Data Protection | Implementation of GDPR compliance measures | In Progress | 2024-05-15
CP-002 | Licensing & Permits | Obtain industry-specific business license | Completed | 2024-04-10
CP-003 | Fiscal Compliance | Tax registration and reporting setup | Pending Review | 2024-06-01
Key Compliance Metrics (Page 1)
KPI | Target | Current Status | Progress %
Regulatory Documentation Complete | 100% | 85% | 85
Audit Readiness Score | 95/100 | 87/100 | 92
Page 1 of Multi-Page Compliance Tracking Template • Generated on:
Compliance Action Plan & Responsibilities
Action Item | Responsible Party | Due Date | Dependencies | Status Update (Comments)
Finalize data encryption protocols | IT Security Team | 2024-06-30 | Legal review completion | In progress – awaiting approval from legal department.
Employee compliance training rollout | Hiring & HR Department | 2024-07-15 | Training material finalization | Pending – materials under draft.
Risk Assessment & Mitigation
Risk ID | Compliance Risk Description | Impact Level | Likelihood | Mitigation Strategy
RK-001 | Data breach due to weak access controls | High | Medium | Implement multi-factor authentication and audit logs.
RK-002 | Lack of updated compliance documentation | Medium | High | Schedule quarterly documentation reviews.
Page 2 of Multi-Page Compliance Tracking Template • Generated on:
Third-Party & Vendor Compliance
Vendor Name | Service Type | Compliance Certifications | Last Audit Date | Status (Valid)
CloudSecure Inc. | Cloud Hosting | ISO 27001, SOC 2 Type II | 2024-03-18 | Valid
DataShield LLC | Data Processing | GDPR Certified, HIPAA Compliant | 2024-05-10 | Pending Renewal Review
Compliance Timeline & Milestones (Page 3)
Milestone | Target Date | Owner | Status
Final compliance report submission to board | 2024-08-31 | CFO & Compliance Officer | Scheduled
Internal audit complete | 2024-10-15 | Compliance Team Lead | Pending Start Date