## Worksheet
Compliance Tracking - Monthly Report October 2023
Compliance Item | Responsible Department | Due Date | Status | Last Updated | Remarks / Actions Required
Data Privacy Policy Review | Legal & Compliance Team | 2023-10-15 | Completed | 2023-10-14 | Policies reviewed and signed off.
Employee Training Completion (Q3) | Human Resources | 2023-10-10 | In Progress | 2023-10-08 | Final 5% pending approval.
Annual Security Audit | IT Security | 2023-10-31 | Pending | 2023-10-05 | Schedule confirmation pending with external auditor.
Regulatory Reporting (FDA) | Quality Assurance | 2023-10-25 | Completed | 2023-10-24 | Submitted successfully via electronic portal.
Health & Safety Inspection | Facilities Management | 2023-10-20 | In Progress | 2023-10-18 | Site walkthrough completed, report in draft.
Vendor Compliance Audit (Top 5) | Procurement | 2023-10-28 | Pending | 2023-10-01 | Schedule pending with vendor approval.
Prepared by: Jane Doe ¦ Compliance Officer Date: October 30, 2023 ¦ Next Review: November 5, 2023