## Worksheet
Compliance Tracking - Finance Template (Team Use)
Item ID | Compliance Requirement | Responsible Team Member | Due Date | Status | Last Updated | Action Required?(Y/N)(If N, explain) | Notes/Comments
FT-2024-001 | Quarterly Financial Audit Compliance | Sarah Johnson (Finance) | 2024-10-31 | In Progress | 2024-09-15 | Y(Preparation ongoing) | Documentation in review; awaiting approval from CFO.
FT-2024-002 | SOX Section 404 Compliance Certification | David Lee (Internal Audit) | 2024-11-30 | Not Started | 2024-09-15 | Y(Initiation phase) | Scheduled kick-off meeting on Oct 1st.
FT-2024-003 | Anti-Money Laundering (AML) Reporting | Lisa Chen (Compliance) | 2024-10-15 | Completed | 2024-10-15 | N(Submitted and approved) | No issues detected in reporting cycle.
FT-2024-004 | Federal Tax Filing Deadline (Form 1120) | Michael Brown (Tax Team) | 2024-11-15 | Pending Review | 2024-09-30 | Y(Finalizing adjustments) | Accounting team reviewing last quarter's expenses.
FT-2024-005 | Regulatory Update: Dodd-Frank Reporting (Schedule 13G) | Amanda Wilson (Legal & Compliance) | 2024-11-30 | Planning | 2024-09-15 | Y(Reviewing new rules) | New rule changes under review for implementation.
Last updated: October 1, 2024 ¦ Template Version: Team Use v1.3