## Worksheet
Compliance Tracking - Analysis View Gantt Chart
Task ID | Task Description | Start Date | End Date | Status | Responsible Team
[6 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul - Dec 2024 (continued)
TASK-001 | Policy Review & Drafting | 2024-01-05 | 2024-03-15 | In Progress | Risk & Compliance
TASK-002 | Stakeholder Consultation | 2024-01-15 | 2024-03-31 | In Progress | Cross-functional Teams
TASK-003 | Internal Audit Preparation | 2024-04-15 | 2024-06-30 | Not Started | Audit Division
MILESTONE-01 | Policy Approval Sign-off | 2024-06-30 | 2024-06-30 | Final Review & Approval
TASK-004 | Training Program Development | 2024-07-15 | 2024-10-31 | Rollout Phase 1
TASK-005 | Implementation & Monitoring | 2024-11-01 | 2024-12-31 | Rollout Phase 2 / Evaluation