## Worksheet
Compliance Tracking - Gantt Chart (Data Version)
Task ID | Task Description | Responsible Party | Start Date | Due Date | Status | Progress (%)
CT-001 | Review Regulatory Requirements | Legal Team | 2024-03-01 | 2024-03-15 | In Progress | 65%
CT-002 | Conduct Internal Audit | Audit Team | 2024-03-10 | 2024-03-31 | Pending Review | 85%
CT-003 | Update Compliance Policies | Compliance Officer | 2024-04-01 | 2024-04-15 | Not Started | 0%
MK-01 | Compliance Approval Sign-Off | Executive Committee | 2024-04-30 | 2024-05-15 | Milestone Reached | 100%
CT-004 | Employee Training Program | HR Department | 2024-05-16 | 2024-06-30 | Not Started | 5%
CT-005 | External Certification Submission | Compliance Manager | 2024-06-15 | 2024-07-31 | Pending Review | 30%
CT-006 | Final Compliance Report Preparation | Data Analysts | 2024-07-15 | 2024-08-31 | Pending Review | 15%
Total Tasks | [5 empty] | 6
Legend:
Task Row- Ongoing or scheduled activities
Milestone- Key achievement point in process
Progress Bar - Visual representation of completion status