## Worksheet
Task ID | Activity/Compliance Item | Responsible Party | Start Date | Due Date | Status | Progress (%)
COM-001 | Complete GDPR Data Audit | Privacy Team | 2024-01-15 | 2024-02-15 | In Progress
COM-002 | Update HIPAA Compliance Documentation | Legal Department | 2024-01-20 | 2024-03-10 | Delayed
COM-003 | Conduct SOC 2 Audit Preparation | Audit Team | 2024-01-10 | 2024-04-30 | On Track
COM-004 | Train Staff on PCI DSS Requirements | HR & Compliance | 2024-02-01 | 2024-03-15 | Not Started
COM-005 | Implement New Data Retention Policy | Data Governance Team | 2024-03-01 | 2024-05-31 | In Progress
COM-006 | Finalize ISO 27001 Certification | Compliance Lead | 2024-04-15 | 2024-12-31 | On Track
COM-007 | Review and Approve Vendor Compliance Agreements | Procurement & Legal | 2024-01-30 | 2024-06-30 | Delayed
COM-008 | Update Cybersecurity Incident Response Plan | IT Security Team | 2024-05-01 | 2024-06-30 | Not Started
COM-009 | Conduct Internal Compliance Review (Q2) | Compliance Manager | 2024-04-15 | 2024-06-30 | In Progress
COM-010 | Document and Report All Compliance Exceptions | Compliance Team | 2024-06-15 | 2024-08-31 | Not Started