## Worksheet
Compliance Tracking - Large Business Gantt Chart
Quarterly Regulatory Compliance Oversight ¦ Reporting Period: Q2 2024
Task / Compliance Item | Responsible Team | Target Start Date | Target End Date | Duration (Days) | Progress | Status
GDPR Data Protection Audit Required by May 31, 2024 | Legal & Compliance | Mar-01-2024 | Apr-30-2024 | 61 |  | Compliant
SOX Internal Control Review Due by Jun-30, 2024 | Finance & Internal Audit | Apr-15-2024 | Jun-15-2024 | 61 |  | On Track
CCPA Customer Rights Processing Continuous compliance with quarterly review | Privacy & Data Governance | Apr-01-2024 | Jun-30-2024 | 91 |  | Compliant
HIPAA Security Assessment Annual requirement; due by May 15, 2024 | IT & Privacy Office | Apr-05-2024 | May-15-2024 | 41 |  | Compliant
ISO 27001 Certification Renewal Preparation phase underway; audit scheduled Jun-25, 2024 | Cybersecurity & Compliance | Feb-15-2024 | Jun-30-2024 | 136 |  | On Track
Compliance Review Board Meeting Final approval for Q2 reporting | Executive Leadership | Jun-18-2024 | Jun-18-2024 | 1 |  | Pending
Financial Reporting Controls Validation Part of SOX and internal financial oversight | Finance & Audit Committee | May-01-2024 | Jun-30-2024 | 61 |  | On Track
Vendor Risk Assessment Update All Tier-1 vendors to be reviewed by Jun-30, 2024 | Risk & Procurement | Mar-15-2024 | Jun-30-2024 | 108 |  | On Track
Generated on June 5, 2024 ¦ This report is for internal compliance tracking purposes only. All dates and status are subject to change based on audit findings and team updates.