## Compliance Tracking Gantt Chart
Compliance Tracking Gantt Chart
Template Type:Gantt Chart
Purpose:Compliance Tracking
Style/Version:Personal Use
Task / Milestone | Start Date | End Date | Duration (Days) | Responsible Party | Status | Gantt Progress (Timeline View)
Regulatory Requirements Review | 2024-04-01 | 2024-04-15 | 15 | Jane Doe | In Progress | 60%
Policy Development & Drafting | 2024-04-16 | 2024-05-10 | 25 | John Smith | In Progress | 35%
Internal Audit Preparation | 2024-05-11 | 2024-05-31 | 21 | Sarah Lee | Delayed | 40%
Training Program Implementation | 2024-06-01 | 2024-06-30 | 30 | Marcus Brown | Completed | 100%
Final Compliance Submission | 2024-07-01 | 2024-07-15 | 15 | Audit Team Lead | In Progress | 80%
Compliance Documentation Finalization | 2024-07-16 | 2024-08-31 | 47 | Linda Chen | In Progress | 55%
Regulatory Feedback Response | 2024-09-01 | 2024-09-30 | 30 | Jane Doe | Delayed (Pending) | 15%
Annual Compliance Review | 2024-10-01 | 2024-10-31 | 31 | John Smith & Team | In Progress | 75%
Note:This Gantt chart template is designed for personal use in compliance tracking. Modify the dates, tasks, and statuses as needed. The visual progress bars represent percentage completion.