## Worksheet
Task | Start Date | End Date | Responsible | Status | Progress (%)
Review Regulatory Requirements | 2023-10-01 | 2023-10-15 | Legal Team | In Progress | 65
Develop Compliance Policy | 2023-10-16 | 2023-11-05 | Compliance Officer | Completed | 100
Train Staff on New Policies | 2023-11-06 | 2023-11-20 | HR Department | On Hold | 40
Conduct Internal Audit | 2023-11-21 | 2023-12-05 | Audit Team | Not Started | 0
Submit Compliance Report to Regulator | 2023-12-06 | 2023-12-15 | Compliance Officer | Not Started | 0
Implement Corrective Actions (if needed) | 2023-12-16 | 2024-01-10 | Project Manager | Not Started | 0