## Worksheet
Compliance Tracking Dashboard - Client View
General Information
Client Name | [Client Name] |  |  | Project ID | [Project ID]
Reporting Period | [Start Date] to [End Date] |  |  | Status | [Status: On Track / At Risk / Delayed]
Compliance Overview
Requirement ID | Requirement Description | Regulatory Standard | Due Date | Status (Current) | Last Updated | Responsible Team/Person | Action Required
RQ-001 | Data Privacy Protection Policy Implementation | GDPR Article 32, HIPAA §164.312 | 2024-08-31 | Compliant | 2024-07-15 | Data Security Team | N/A
RQ-002 | Annual Cybersecurity Audit Completion | ISO/IEC 27001:2022, NIST SP 800-53 | 2024-11-30 | In Progress | 2024-07-18 | Compliance Office | Schedule audit with third party by 2024-09-15
RQ-003 | Employee Training on Compliance Protocols (Annual) | OSHA, SOX Section 404 | 2024-12-15 | Not Started | 2024-06-30 | HCM Department | Develop training modules and schedule sessions by 2024-10-31
RQ-004 | Documentation of Risk Assessments for Third Parties | SOX, SEC Rule 17a-4(f) | 2025-01-31 | In Review | 2024-07-25 | Risk Management Team | Finalize documentation and submit for approval by 2024-08-31
RQ-005 | Incident Response Plan Testing (Annual) | PCI DSS Requirement 12.8, NIST SP 800-61 | 2024-12-31 | On Track | 2024-07-16 | Cybersecurity Team | Schedule test drill by 2024-11-30
Compliance Summary (Current Period)
Total Requirements | 5 | Compliant | 1 (20%) | In Progress | 1 (20%) | Pending/Not Started | 3 (60%)
Action Items & Next Steps
• Complete training module development by October 31, 2024. • Finalize third-party risk assessment documentation by August 31, 2024. • Schedule cyber incident response test drill before December 15, 2024. • Engage external auditor for annual cybersecurity audit by September 15, 2024.
Notes & Comments
This compliance tracking report is for internal client review. All data sourced from the compliance management system as of July 26, 2024. Please verify and update status regularly.