## Worksheet
Compliance Tracking - Maintenance Log - Analysis View
Maintenance ID | Asset Name | Location | Maintenance Type | Scheduled Date | Actual Completion Date | Status | Compliance Level
MNT-2024-001 | Fire Suppression System | Building A, Floor 3 | Preventive Maintenance | 2024-05-15 | 2024-05-14 | Compliant | Level 1 (High)
MNT-2024-003 | Emergency Lighting System | Corridor & Stairwells | Inspection & Testing | 2024-05-18 |  | Pending | Level 1 (High)
MNT-2024-007 | HVAC Unit #5 | Server Room, Basement | Preventive Maintenance | 2024-05-16 | 2024-05-17 | Compliant | Level 2 (Medium)
MNT-2024-015 | Security Camera Network | Entrance & Exits, Parking Area | Clean & Calibration | 2024-05-19 |  | Overdue (1 Day) | Level 1 (High)
MNT-2024-023 | Water Heater System | Utility Room, Floor 1 | Pump Inspection & Pressure Test | 2024-05-17
MNT-2024-031 | Generator Set (Backup Power) | Electrical Substation, Ground Floor | Load Bank Test & Fuel Check | 2024-05-15
MNT-2024-044 | Door Access Control System | Main Lobby & Restricted Zones | Firmware Update & Audit | 2024-05-18
MNT-2024-056 | Exhaust Ventilation (Kitchen) | Kitchen Area, Floor 2 | Filter Replacement & Duct Cleaning | 2024-05-19
MNT-2024-068 | Fire Extinguishers (All Units) | Per Floor & Common Areas | Inspection & Pressure Test | 2024-05-17
MNT-2024-089 | Emergency Evacuation Signage | Corridors & Exit Paths | Replacement & Verification | 2024-05-16
Overdue (4 Days)
Compliance Summary
Total Records: | 10
Compliant: | 3 (30%)
Pending: | 4 (40%)
Overdue: | 3 (30%)
Note: Overdue entries require immediate attention. Compliance Level indicates criticality of the asset.