## Worksheet
Compliance Tracking - Annual Project Plan
Annual Review Period: January 2024 – December 2024 ¦ Prepared on: October 5, 2023
Item ID | Compliance Requirement | Responsible Department | Due Date | Status | Action Plan / Notes
C-001 | ISO 9001:2015 Certification Renewal | Quality Assurance | March 31, 2024 | Pending Review | Final documentation submission scheduled for February 15.
C-002 | Data Protection Compliance (GDPR) | Legal & IT | April 30, 2024 | In Progress | Annual audit preparation underway; risk assessment updated.
C-003 | Environmental Management System (ISO 14001) | Sustainability Office | June 30, 2024 | On Track | Internal audit scheduled for May 20.
C-004 | Workplace Safety Audit (OSHA) | HR & Facilities | July 31, 2024 | In Progress | Safety training completed; corrective actions pending.
C-005 | Financial Reporting Compliance (SOX) | Finance & Internal Audit | September 30, 2024 | On Track | Quarterly reviews completed; documentation in final review phase.
C-006 | Cybersecurity Policy Update & Training | IT Security | October 31, 2024 | On Track | Training module developed; rollout planned for October.
C-007 | Employee Diversity & Inclusion Report | HR Department | November 30, 2024 | In Progress | Data collection in progress; analysis expected by October 15.
C-008 | Annual Compliance Training Completion | Training & Development | December 31, 2024 | Pending Review | All employees must complete training by year-end; tracking system active.
C-009 | Regulatory Disclosure for Annual Report | Corporate Affairs | January 15, 2025 (Post-Year-End) | Pending Review | Preparation underway; legal team in final approval stage.
C-010 | Internal Control Framework Evaluation | Internal Audit | February 28, 2025 (Post-Year-End) | Pending Review | Fiscal year review initiated; gap analysis in progress.
© 2023 Company Name. All rights reserved. This document is for internal compliance tracking and may not be distributed without authorization.